## Capstone Timeline
|  | Capstone Start Date | 2023-01-13
Week | Session Plan | Milestones | Release Date | Capstone Mentorship Session |  | Submissions by Students
Sat or Sun
Week 0 | Capstone Orientation | Release Problem Statement (PO). | 2023-01-06 | 2023-01-14
Release group list (PO).
Release Interim report template (PO).
|  | Release Final report template (PO). |  | Capstone Orientation Session (Saturday)
Release Milestones/weekly plan (PO).
Expectation setting (PO).
Week 1 | Capstone Mentoring Session -1 : Discussion of Problem Statement, Delegation of responsibilities among team members, Planning the progress and approach to capstone | Interim Report Release | Interim Report Submission Release | 2023-01-21 | 2023-01-22 | -
Problem Statement Discussion.
Dataset discussion
|  | Inputs on how to approach this problem statement. | 2023-01-20
Week 2 | No session | Milestone 1: | - | PM Check IN
1. Data exploration and preproccessed data ready for model building.
2. Interim report 1st draft upto data preprocessing.
Week 3 | Capstone Mentoring Session 2 - Review of Notebook and Interim Report. Point out errors, suggest alternate methods, Doubt clarification, unblocking roadblocks. | Milestone 1: |  | 2023-02-04 | 2023-02-05 | Interim Report Submission Due
1. Train a base model.
2. Include Base model in Intreim report.
|  | 3. Share notetbook & Interim report with mentor 1 day before session. |  |  |  | 2023-02-05
4. Mentor to share review comments with the group during session.
5. Groups to incorporate the changes and submit Interim report for evaluation.
Week 4 | No session | Final Report Release | Final Report Release | No Session
1. Experimenting with different approaches / algorithms / architectures to improve performance of the model.
|  | 2. Performane improvement using paramters / hyperparameters tuning. | 2023-02-10
3. Compare various model's performance to conclude best performing model.
Week 5 | Capstone Mentoring Session - 3 - Validation of the final notebook & final report and suggestions, inputs, correction before submission | Milestone 2: | - | 2023-02-18 | 2023-02-19 | --
1. Update all progress in final report.
2. Share copy of notebook and final report with mentor 1 day before session.
3. Discuss additional inputs from mentor for performance improvement.
4. Discuss additional inputs from mentor for final report improvement.
Week 6 | Capstone Mentoring Session - 4- Presentation of capstone project by students to mentor | Milestone 2: | - | 2023-02-25 | 2023-02-26 | Final Report Submission Due
1. Showcase all the improvements achieved during last week to the mentor.
|  | 2. Submit Final report and capstone work for evaluation. |  |  |  | 2023-02-26